## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | Configure a customer-support session and select the required interaction mode so that the appropriate support workflow can be started. | Must Have | — | Karanam Charvi | 3- Completed
1 | 1 | US-02 | Use Simulator Mode to practice customer-support conversations with an AI-generated customer. | Must Have | US-01 | Karanam Charvi | 3- Completed
1 | 1 | US-03 | Maintain conversation context across multiple turns so that AI guidance remains relevant throughout the interaction. | Must Have | US-01 | Karanam Charvi | 3- Completed
1 | 1 | US-04 | Build a Support Knowledge Base so that relevant customer-support information can be retrieved during an interaction. | Must Have | US-01 | Karanam Charvi | 3- Completed
2 | 2 | US-05 | Analyze customer intent and sentiment so that the support agent can understand the customer's issue and emotional state. | Must Have | US-03 | Karanam Charvi | 3- Completed
2 | 2 | US-06 | Retrieve relevant support knowledge using RAG so that responses are supported by appropriate knowledge. | Must Have | US-04 | Karanam Charvi | 3- Completed
2 | 2 | US-07 | Provide relevant knowledge recommendations according to the customer's current issue. | Must Have | US-06 | Karanam Charvi | 3- Completed
3 | 3 | US-08 | Monitor escalation risk so that potential customer escalations can be identified during the interaction. | Must Have | US-05 | Karanam Charvi | 3- Completed
3 | 3 | US-09 | Provide AI-generated response suggestions and coaching guidance to help the support agent respond effectively. | Must Have | US-05, US-06 | Karanam Charvi | 3- Completed
3 | 3 | US-10 | Coordinate the specialized AI agents through an orchestration workflow so that the interaction is processed systematically. | Must Have | US-05, US-06, US-08 | Karanam Charvi | 3- Completed
3 | 3 | US-11 | Provide a Live Support Console displaying the conversation, coaching guidance and knowledge recommendations in one interface. | Must Have | US-07, US-09, US-10 | Karanam Charvi | 3- Completed
3 | 3 | US-12 | Allow customer messages to be entered manually so that interactions can be analyzed without using the simulator. | Should Have | US-05, US-09 | Karanam Charvi | 3- Completed
4 | 4 | US-13 | Replay previous customer-support conversations so that interactions can be reviewed turn by turn. | Should Have | US-03, US-11 | Karanam Charvi | 3- Completed
4 | 4 | US-14 | Generate a post-interaction summary and performance evaluation so that the completed conversation can be reviewed. | Must Have | US-05, US-09, US-10 | Karanam Charvi | 3- Completed
4 | 4 | US-15 | Provide history and analytics so that previous sessions and interaction performance can be reviewed. | Should Have | US-13, US-14 | Karanam Charvi | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 205 | 12 | 22 | 23 | 28 | 23 | 28 | 13 | 16 | 20 | 7 | 7 | 6 | 0 | 0
SPRINT 1 BACKLOG
US-01 | 1 | Study customer support workflow, RAG and multi-agent architecture | 2026-07-06 | 2026-07-07 | Karanam Charvi | Others | 3-Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 2 | Design system architecture and agent responsibilities | 2026-07-07 | 2026-07-09 | Karanam Charvi | Design | 3-Completed | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 3 | Design orchestration flow and conversation state | 2026-07-09 | 2026-07-10 | Karanam Charvi | Design | 3-Completed | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 4 | Build session configuration and interaction-mode selection | 2026-07-10 | 2026-07-13 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | 5 | Prepare and ingest support knowledge documents | 2026-07-13 | 2026-07-14 | Karanam Charvi | Coding | 3-Completed | 5 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | 6 | Implement paragraph-aware chunking | 2026-07-14 | 2026-07-15 | Karanam Charvi | Coding | 3-Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | 7 | Generate embeddings and build vector index | 2026-07-15 | 2026-07-16 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | 8 | Implement knowledge retrieval and validate retrieved content | 2026-07-16 | 2026-07-17 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-02 | 1 | Implement Customer Simulator Agent | 2026-07-20 | 2026-07-21 | Karanam Charvi | Coding | 3-Completed | 7 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | 2 | Implement scenario, persona and difficulty handling | 2026-07-21 | 2026-07-23 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | 3 | Maintain customer conversation state across turns | 2026-07-23 | 2026-07-24 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | 4 | Implement Intent and Sentiment Analysis Agent | 2026-07-24 | 2026-07-27 | Karanam Charvi | Coding | 3-Completed | 7 | 0 | 0 | 0 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | 5 | Implement intent, sentiment and emotional-state analysis | 2026-07-27 | 2026-07-28 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | 6 | Implement Knowledge Recommendation Agent | 2026-07-28 | 2026-07-30 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | 7 | Integrate knowledge retrieval with the agent workflow | 2026-07-30 | 2026-07-31 | Karanam Charvi | Integration | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0
US-02/06 | 8 | Test simulator realism and knowledge retrieval | 2026-07-31 | 2026-07-31 | Karanam Charvi | Testing | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
SPRINT 3 BACKLOG
US-09 | 1 | Implement Coaching and Response Suggestion Agent | 2026-08-03 | 2026-08-04 | Karanam Charvi | Coding | 3-Completed | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | 2 | Implement response, tone and communication guidance | 2026-08-04 | 2026-08-06 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | 3 | Implement Escalation Risk Monitor Agent | 2026-08-06 | 2026-08-07 | Karanam Charvi | Coding | 3-Completed | 7 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | 4 | Implement escalation scoring and risk alerts | 2026-08-07 | 2026-08-10 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | 5 | Integrate specialized agents using LangGraph orchestration | 2026-08-10 | 2026-08-11 | Karanam Charvi | Integration | 3-Completed | 8 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | 6 | Build three-panel Live Support Console | 2026-08-11 | 2026-08-13 | Karanam Charvi | Coding | 3-Completed | 8 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | 7 | Integrate conversation, coaching and knowledge panels | 2026-08-13 | 2026-08-14 | Karanam Charvi | Integration | 3-Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0
US-12/13 | 8 | Implement Manual Mode and Replay Mode | 2026-08-14 | 2026-08-14 | Karanam Charvi | Coding | 3-Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-14 | 1 | Implement Post-Interaction Summary Agent | 2026-08-17 | 2026-08-18 | Karanam Charvi | Coding | 3-Completed | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | 2 | Implement sentiment journey and resolution-quality analysis | 2026-08-18 | 2026-08-19 | Karanam Charvi | Coding | 3-Completed | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | 3 | Generate personalized coaching recommendations | 2026-08-19 | 2026-08-19 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | 4 | Develop Performance Analytics module | 2026-08-19 | 2026-08-20 | Karanam Charvi | Coding | 3-Completed | 7 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | 5 | Implement history and session performance tracking | 2026-08-20 | 2026-08-20 | Karanam Charvi | Coding | 3-Completed | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | 6 | Perform end-to-end testing of all interaction modes | 2026-08-20 | 2026-08-21 | Karanam Charvi | Testing | 3-Completed | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | 7 | Test multi-agent, RAG and post-interaction workflow | 2026-08-21 | 2026-08-21 | Karanam Charvi | Testing | 3-Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
US-15 | 8 | Prepare technical documentation and final project report | 2026-08-21 | 2026-08-21 | Karanam Charvi | Documentation | 3-Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2026-07-06 | Need to finalize the system architecture and responsibilities of the AI agents | Reviewed project requirements and finalized the architecture, agent roles and workflow
1 | 2026-07-13 | Support knowledge needed to be prepared properly for RAG processing | Prepared the knowledge documents and finalized the chunking, embedding and retrieval approach
2 | 2026-07-20 | Customer Simulator needed to maintain realistic behavior across conversation turns | Refined the simulator scenario, persona and conversation-state handling
2 | 2026-07-27 | Retrieved knowledge needed to be relevant to the current customer issue | Tested RAG retrieval with support scenarios and refined the retrieval process
3 | 2026-08-03 | Multiple AI agents needed to work together while maintaining conversation context | Integrated the agents through the LangGraph orchestration workflow
3 | 2026-08-10 | Live coaching, conversation and knowledge information needed to work together in the support console | Integrated and tested the conversation, coaching and knowledge panels
4 | 2026-08-17 | Post-interaction summary and analytics needed to be integrated with the completed workflow | Integrated the summary, analytics and session-related components
4 | 2026-08-20 | Final end-to-end testing was required across all interaction modes | Performed final testing, fixed identified issues and completed the project

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-07-06 | 2026-07-17 | Karanam Charvi | Start testing individual components earlier | Delay integration testing | Keep the system modular and organized | Started validating components before moving to integration
2 | 2 | 2026-07-20 | 2026-07-31 | Karanam Charvi | Start testing RAG retrieval with more scenarios | Make changes without immediate testing | Continue testing agent outputs with different inputs | Added more scenario-based checks for simulator and RAG
3 | 3 | 2026-08-03 | 2026-08-14 | Karanam Charvi | Start validating agent communication at each stage | Postpone workflow integration | Continue maintaining conversation context | Validated agent outputs and improved LangGraph workflow integration
4 | 4 | 2026-08-17 | 2026-08-21 | Karanam Charvi | Start final end-to-end testing before completion | Leave final testing until the end | Continue systematic testing and documentation | Completed end-to-end testing, fixed issues and finalized documentation