## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Karanam Charvi | 2026-07-10 | Session configuration did not retain the selected interaction mode correctly | 1 | Karanam Charvi | Functional | Corrected the session configuration and verified mode selection | 2026-07-11 | Closed | Retested with the available interaction modes
2 | Karanam Charvi | 2026-07-15 | Knowledge content was not divided into suitable chunks during RAG ingestion | 1 | Karanam Charvi | RAG / Data | Adjusted the knowledge chunking process and reprocessed the content | 2026-07-16 | Closed | Knowledge chunks were rechecked after correction
3 | Karanam Charvi | 2026-07-27 | Customer simulator required improvement in maintaining context across conversation turns | 2 | Karanam Charvi | AI / Functional | Improved conversation-state handling in the simulator workflow | 2026-07-28 | Closed | Simulator was retested across multiple turns
4 | Karanam Charvi | 2026-07-30 | RAG retrieval did not consistently return the most relevant support information for some queries | 2 | Karanam Charvi | RAG / Functional | Reviewed and refined the retrieval process and tested it with support queries | 2026-07-31 | Closed | Retrieval was retested with multiple scenarios
5 | Karanam Charvi | 2026-08-11 | Agent outputs were not correctly passed between some stages of the LangGraph workflow | 3 | Karanam Charvi | Integration | Corrected the workflow state and agent-to-agent data flow | 2026-08-12 | Closed | Multi-agent workflow was retested
6 | Karanam Charvi | 2026-08-13 | Coaching and knowledge information required correction in the live support console display | 3 | Karanam Charvi | UI / Integration | Corrected the frontend integration and verified the displayed information | 2026-08-14 | Closed | Live support console was retested
7 | Karanam Charvi | 2026-08-20 | Final end-to-end workflow required corrections before project completion | 4 | Karanam Charvi | Integration / Functional | Fixed the identified integration issues and performed final end-to-end testing | 2026-08-21 | Closed | Final workflow completed successfully

## Sheet2
Logical
User Interface
Maintainability
Standards
Others